## Sheet1
Task ID | Task Name | Sub Task | Task Description | Status
AVIMA_01 | Login Screen |  |  | Completed
AVIMA_02 | File | Yet to deside | Yet to deside | Pending
AVIMA_03 | Stock | Search |  | Completed
|  | Create |  | Completed
|  | Edit |  | Completed
|  | Delete |  | Completed
|  | Return By Customer | UI Design completed. DB and BL layer pending | Pending
Purchase Order Tracking and Deleting
|  | Return To Supplier | UI Design completed. DB and BL layer pending | Pending
AVIMA_4 | Billing | Invoice |  | Completed
|  | Auto populate Item details on bar code scanner |  | Completed
|  | Auto poupulate customer details |  | Completed
|  | Temporary Invoice Save and Retrieve and continue billing - Hold |  | Pending
|  | Should be able search customer on name text box itself no grid required - Min 3 characters |  | Completed
|  | Multi page printing in invoice - Maximum 300 items |  | Pending
|  | Delete billing search criteria would be date |  | Pending
|  | Show Invoice |  | Completed
AVIMA_5 | Report | Stock Report | Yet to deside | Pending
|  | Daily Sales Report | Yet to deside | Pending
|  | Deleted Bills Report | Yet to deside | Pending
|  | Deleted Stock Report | Yet to deside | Pending
|  | Stock Return Report | Yet to deside | Pending
AVIMA_6 | Maintanance | Repair |  | Completed
|  | Show Repair |  | Completed
AVIMA_7 | Administration | User |  | Completed
|  | Supplier |  | Completed
|  | Customer |  | Completed
AVIMA_8 | Help | Help screen | Pending | Pending
AVIMA_9 | Logo | Design | Pending | Pending
AVIMA_10 | Genaral | Bind only required columns to the grid every where, good way of clearing grid rows | Pending | Pending
AVIMA_11 | Database | Add two extra columns for future usage | Pending | Pending